## Overall Status
JEA Surplus Property Status Tracker
Property Address | Common Name | Status
9201 Altantic Blvd | Coggin Dealership | Agency Routing
13601 Normandy Blvd | Cecil Commerce Center-North | Planning
1215 Talleyrand Ave. | KGS | Planning
21 W. and W. Church St./421 Laura St. | Downtown Campus Plaza I, II, III | Planning
758 St. Johns Bluff Rd. N | Abandoned well | Agency Routing

## Workbook
JEA Surplus Property Status Tracker
Property | Common Name | RE # | Acreage (Estimated) | County | Status | Internal Review to approve disposition | Survey easements or retained property | Appraisal | COJ/Government Notification/Option | Bid Published | Bid Closed/Contract Awarded | Board or Awards Committee Approval | Closing | Status
9201 Altantic Blvd | Coggin Dealership | 123041-0000 | 5.07 | Duval | Appraisal Ordered | 1.7.19 | 2.28.19 | 4.25.19 | 4.26.19 |  |  |  |  | Planning
13601 Normandy Blvd | Cecil Commerce Center-North | 001982-10000 | 250 | Duval | Planning | 4.10.19 | [7 empty] | Internal Routing
1215 Talleyrand Ave. | KGS | 131420-0000 | 26.5 | Duval | Planning | [8 empty] | Agency Routing
21 W. and W. Church St./421 Laura St. | Downtown Campus Plaza I, II, III | 073863-0000 073863-0000 073868-0000 | 3.26 | Duval | Planning | [8 empty] | Appraisal Ordered
758 St. Johns Bluff Rd. N. | Abandoned Well | 161864-0000 | 0.15 | Duval | Agency Routing | 8.16.18 | N/A | N/A | 4.2.19 |  |  |  |  | Procurement
Marketing
Closing

## Timeline
Internal Review to approve disposition | Survey easements or retained property | Appraisal | COJ/Government Notification/Option | Bid Published | Bid Closed/Contract Awarded | Board or Awards Committee Approval | Closing
1 week | 2-4 weeks | 4-6 weeks | 2 weeks | 1 week | 4 weeks | 4 weeks | 90—120 days