## Sheet1
* While this document is meant to track majority pre-Board Meeting activities, all timing and activties must be confirmed and aligned with Scenario 3 plan
Scenario 3 Communications Tracker: Board Meeting Tuesday, July 23
Activity ¦ Stakeholder | 2019-07-08 | 2019-07-09 | 2019-07-10 | 2019-07-11 | 2019-07-12 | 2019-07-15 | 2019-07-16 | 2019-07-17 | 2019-07-18 | 2019-07-19 | 2019-07-22 | 2019-07-23 | 7/24 on | Lead
Hammer out, finalize Scenario 3 and set realistic timeline, steps for implementation | [13 empty] | SLT
Develop and finalize Scenario 3 PowerPoint presentation
Update overall key messages and tough Q&A | [13 empty] | Communications | bar: 2019-07-09
Develop Scenario 3 fact sheet
Mail-out finalized Board Meeting packet
Target and formally agree on list of internal and external in-person stakeholder meetings and events (employees? Unions? City Council members? Civic Council? Chamber leadership? Nobody pre-Board Meeting?)
Develop segmented "what's in it for me" messages per stakeholder
Schedule and brief Mayor
Develop and post July Aaron LinkedIn blog: "Strategic planning during times of uncertainty" | bar: 2019-07-18
Develop and post daily thought-leadership social content (Aaron Twitter, LinkedIn) | [12 empty] | X | bar: 2019-07-09 to 2019-07-23
Develop and post daily JEA-related consumer social content (corporate Twitter, LinkedIn as appropriate)
Confirm JEA spokespersons for all approved internal and external meetings and communications
Schedule day-of, post-Board Meeting 45 minute 1:1s with key reporters
Develop and distribute Scenario 3-specific Currents (personalize from SLT?)
Develop RFP, RFI, RFQ, ITN (?) for implementation of Scenario 3
Re-schedule on-camera media training for Aaron, April and Julio
Confirm consistent message for all post-Board Meeting events, speaking opportunties (i.e. 7/30 JAXUSA) | [12 empty] | X
Develop plan for and stick to monthly key reporter briefings (as Scenario 3 is implemented) | [12 empty] | X
Develop paid strategy to support post-Scenario 3 implentation (reference Integrated Strategic Plan) | [12 empty] | X
Ongoing social content (reference Integrated Strategic Plan) | [12 empty] | X
Ongoing national media outreach (reference Integrated Strategic Plan) | [12 empty] | X